## Sheet1
Team Scorpion
Developers: B M M Bari - 1711384042 [ CSE327 Section 07 ] Aminul Islam Joy - 1711867642 [ CSE327 Section 07 ] Rafiul Hasan - 1712524042 [ CSE327 Section 07 ]
Product Backlog: "House Rental and Management System"
User Story:
ID | As a… | I want to be able to… | So that… | Priority | Sprint | Status
1 | User | Keep Track on the rent | I don't loose the calculation and know my exact income from the house rent. | 1 | 1 | In Progress
2 | User | Update or Delete informations | I can keep the perfect calculation. | 1 | 1 | In Progress
3 | User | Collect the Utility Bill | I don't have to keep tracks on the bills manually. | 2 | 2 | In Progress
4 | User | have the information of the tenants | according the the security department of bangladesh I will be able have and send the information as their requirement. | 3 | 2 | In Progress
5 | User | have the information of my flats with all facilities. | I can handle facilities and show them to the tenants. | 4 | 3 | To be started
6 | User | track maintainance time | nothing can go wrong without having maintainance. | 5 | 4 | To be started
7 | User | Count my annual tax | I can deposit my annual tax without any extra pressure. | 6 | 5 | To be started
8 | User | pay my house loan installment | the application will remind me to pay the installment on time with proper amount to pay. | 7 | 6 | To be started
9 | User | locate the house store | I can keep track on the back product for house renocation work. | 8 | 7 | To be started
10 | User | pay guard bill, maintainance worker bill | everyone gets paid on time with exact amount | 9 | 8 | To be started