## Sheet1
Team Scorpion
Developers: B M M Bari - 1711384042 [ CSE327 Section 07 ] Aminul Islam Joy - 1711867642 [ CSE327 Section 07 ] Rafiul Hasan - 1712524042 [ CSE327 Section 07 ]
"House Rental and Management System"
Sprint Backlog:
ID | User Story | Tasks | Day 01 | Day 02 | Day 03 | Day 04 | Day 05 | Day 06 | Day 07
1 | As a user I want to be able to keep track on the rent, So that I don't loose the calculation and know my exact income from the house rent. | Design user interface for dashboard | 5 | 0 | 0 | 0 | 0 | 0 | 0
|  | write code for dashboard page | 0 | 6 | 0 | 0 | 0 | 0 | 0
|  | Create database table for storing info | 0 | 0 | 3 | 2 | 0 | 0 | 0
|  | Connect dashboard page with database | 0 | 0 | 0 | 0 | 3 | 0 | 0
|  | Test the reservation page | 0 | 0 | 0 | 0 | 0 | 1 | 0
2 | As a user I want to be able to have all the informations of the tenants so that I can have the information and provide to the government officer if needed. (As per Government Security Rule). | Design interface for information page | 6 | 0 | 0 | 0 | 0 | 0 | 0
|  | Write code for information page | 0 | 6 | 0 | 0 | 0 | 0 | 0
|  | Create database table for Information. | 0 | 0 | 4 | 0 | 0 | 0 | 0
|  | Connect information with database | 0 | 0 | 0 | 2 | 0 | 0 | 0
|  | Write code for query/seach option | 0 | 0 | 0 | 0 | 3 | 3 | 0
|  | Run a test for information page | 0 | 0 | 0 | 0 | 0 | 0 | 1